# DEVELOPMENT SCHEDULES & PROJECT TIMELINES

Purpose: This exhibit provides standardized development schedules and milestone templates for Tiny Village™ projects. Actual project schedules will vary based on project size, location, permitting requirements, financing, contractor availability, and market conditions.

MASTER DEVELOPMENT TIMELINE

PHASE 1 – PROJECT INITIATION

Estimated Duration: 30–90 Days

Activities

□ Define Project Vision

□ Establish Development Entity

□ Secure Domain & Branding

□ Develop Initial Business Plan

□ Assemble Development Team

□ Conduct Preliminary Market Analysis

□ Establish Project Budget

Milestone: Project Approval to Proceed

PHASE 2 – SITE SELECTION & DUE DILIGENCE

Estimated Duration: 60–180 Days

Activities

□ Identify Candidate Sites

□ Preliminary Zoning Review

□ Utility Availability Review

□ Environmental Assessment

□ Site Survey

□ Geotechnical Investigation

□ Preliminary Site Planning

□ Land Purchase Negotiations

Milestone: Land Acquisition Approval

PHASE 3 – ENTITLEMENTS & PERMITTING

Estimated Duration: 90–270 Days

Activities

□ Concept Site Plan

□ Municipal Meetings

□ Engineering Design

□ Utility Coordination

□ Stormwater Design

□ Traffic Analysis

□ Zoning Approval

□ Site Plan Approval

□ Building Permit Submission

Milestone: Permits Approved

PHASE 4 – FINANCING & CAPITALIZATION

Estimated Duration: 60–180 Days

Activities

□ Investor Package Preparation

□ Financial Modeling

□ Pro Forma Development

□ Capital Raising Campaign

□ Loan Applications

□ Lender Due Diligence

□ Closing Documentation

Milestone: Financial Close

PHASE 5 – INFRASTRUCTURE DEVELOPMENT

Estimated Duration: 90–240 Days

Activities

□ Site Clearing

□ Earthwork

□ Utility Installation

□ Water Systems

□ Sewer Systems

□ Electrical Distribution

□ Fiber Internet

□ Roads

□ Parking Areas

□ Drainage Improvements

Milestone: Infrastructure Completion

PHASE 6 – VERTICAL CONSTRUCTION

Estimated Duration: 90–180 Days

Activities

□ Home Installation

□ Utility Connections

□ Exterior Improvements

□ Community Buildings

□ Landscaping

□ Signage Installation

□ Final Inspections

Milestone: Certificate of Occupancy

PHASE 7 – LEASE-UP & OCCUPANCY

Estimated Duration: 90–180 Days

Activities

□ Marketing Campaign

□ Resident Applications

□ Screening Process

□ Lease Execution

□ Move-In Scheduling

□ Resident Orientation

Milestone: 95% Occupancy

PHASE 8 – STABILIZED OPERATIONS

Estimated Duration: Ongoing

Activities

□ Property Management

□ Maintenance Programs

□ Reserve Funding

□ Investor Reporting

□ HOA Governance

□ Capital Planning

Milestone: Operational Stabilization

SAMPLE 24-MONTH DEVELOPMENT SCHEDULE

| Phase | Months |
| --- | --- |
| Project Planning | 1-2 |
| Site Selection | 2-4 |
| Due Diligence | 3-6 |
| Land Acquisition | 4-6 |
| Entitlements | 5-10 |
| Financing | 6-10 |
| Infrastructure | 10-15 |
| Home Installation | 14-18 |
| Community Amenities | 15-19 |
| Lease-Up | 18-24 |
| Stabilization | 24+ |

GANTT-STYLE DEVELOPMENT MATRIX

TASK M1 M2 M3 M4 M5 M6 M7 M8 M9 M10 M11 M12

Project Planning ■ ■

Site Selection ■ ■

Due Diligence ■ ■ ■

Land Acquisition ■ ■

Entitlements ■ ■ ■ ■

Engineering ■ ■ ■

Financing ■ ■ ■

Infrastructure ■ ■ ■ ■

Construction ■ ■ ■

Amenity Construction ■ ■

Lease-Up ■ ■ ■

Stabilization ■

PERMITTING SCHEDULE TEMPLATE

| Activity | Target Date | Actual Date |
| --- | --- | --- |
| Zoning Review | _____ | _____ |
| Pre-Application Meeting | _____ | _____ |
| Site Plan Submission | _____ | _____ |
| Engineering Approval | _____ | _____ |
| Utility Approval | _____ | _____ |
| Building Permit Submission | _____ | _____ |
| Permit Approval | _____ | _____ |
| Final Inspection | _____ | _____ |
| CO Issued | _____ | _____ |

CONSTRUCTION MILESTONE SCHEDULE

| Milestone | Planned Date | Actual Date |
| --- | --- | --- |
| Notice to Proceed | _____ | _____ |
| Site Clearing | _____ | _____ |
| Utilities Installed | _____ | _____ |
| Roads Completed | _____ | _____ |
| Foundations Complete | _____ | _____ |
| Homes Delivered | _____ | _____ |
| Home Installation Complete | _____ | _____ |
| Landscaping Complete | _____ | _____ |
| Final Inspection | _____ | _____ |
| Occupancy Approval | _____ | _____ |

LEASE-UP SCHEDULE

| Activity | Target Date |
| --- | --- |
| Marketing Launch | _____ |
| Applications Open | _____ |
| First Lease Signed | _____ |
| First Move-In | _____ |
| 25% Occupancy | _____ |
| 50% Occupancy | _____ |
| 75% Occupancy | _____ |
| 95% Occupancy | _____ |

INVESTOR REPORTING MILESTONES

Monthly

□ Construction Update

□ Budget Update

□ Occupancy Report

□ Cash Flow Report

Quarterly

□ Investor Letter

□ KPI Dashboard

□ Strategic Review

Annually

□ Financial Audit

□ Budget Adoption

□ Reserve Fund Review

□ Investor Meeting

DEVELOPMENT CHECKPOINTS

GO / NO-GO DECISION #1

Site Feasibility Complete

□ Approved

□ Deferred

□ Rejected

GO / NO-GO DECISION #2

Entitlements Achieved

□ Approved

□ Deferred

□ Rejected

GO / NO-GO DECISION #3

Financing Secured

□ Approved

□ Deferred

□ Rejected

GO / NO-GO DECISION #4

Construction Completion

□ Approved

□ Deferred

□ Rejected

CRITICAL PATH ITEMS

Highest-Risk Schedule Activities

□ Land Acquisition

□ Zoning Approval

□ Utility Capacity

□ Financing Approval

□ Contractor Procurement

□ Infrastructure Completion

□ Permit Issuance

□ Home Delivery

□ Occupancy Stabilization

PROJECT CLOSEOUT SCHEDULE

□ Final Inspections

□ Punch List Completion

□ Warranty Documentation

□ Asset Inventory Update

□ Reserve Study Update

□ HOA Turnover Documentation

□ Investor Final Report

□ Lessons Learned Review

DOCUMENT RETENTION

Development Schedules: Permanent Retention

Board-Approved Schedules: Permanent Archive

Construction Schedules: Permanent Archive

Investor Reporting Schedules: Permanent Archive

Document Classification: Development Planning Record